## Index and Info
Sheet No. | Sheet Name | Description | Priority
1 | Index and Info | — | High
2 | Customer | User Story document for user type Customer (Buyer) | Medium
3 | Seller | User Story document for user type Seller | Low
4 | Admin | User Story document for user type Admin | Status
5 | Sprint 1 | Sprint Plan document including list of tasks | To-Do
6 | Sprint 2 | Sprint Plan document including list of tasks | In-progress
7 | Sprint 3 | Sprint Plan document including list of tasks | Done
8 | Sprint 4 | Sprint Plan document including list of tasks | Incomplete
9 | Sprint 5 | Sprint Plan document including list of tasks | Backlog
10 | Sprint 6 | Sprint Plan document including list of tasks | Sprint Status Workflow
To-do -> In-progress -> Done
To-do -> In-progress -> Incomplete -> Backlog -> Move to Next sprint

## Customer
# | User Story Summary | Issue Type | Status | Priority | Sprint | Comment
1 | As a customer, I want to sign up so I can create my CampusHub account. | Story | Done | High | Sprint 1
2 | As a customer, I want to log in using email & password to access the platform. | Story | Done | High | Sprint 1
3 | As a customer, I want to view and edit my profile details. | Story | Done | High | Sprint 2
4 | As a customer, I want to browse all available product listings. | Story | Done | High | Sprint 2
5 | As a customer, I want to search listings using keywords, categories, and filters. | Story | Done | High | Sprint 2
6 | As a customer, I want to view detailed information for a listing including price, condition, and seller info. | Story | Done | High | Sprint 3
7 | As a customer, I want to message the AI chatbot to help me find items quickly. | Story | Done | High | Sprint 4
8 | As a customer, I want to upload images when creating my own listings (if I become a seller). | Story | Done | High | Sprint 3
9 | As a customer, I want to report inappropriate listings. | Story | Done | High | Sprint 4
10 | As a customer, I want to log out of the application securely. | Story | Done | High | Sprint 1

## Seller
# | User Story Summary | Issue Type | Status | Priority | Sprint | Comment
1 | As a seller, I want to sign up and create a seller profile. | Story | Done | High | Sprint 1
2 | As a seller, I want to log in securely so I can manage my listings. | Story | Done | High | Sprint 1
3 | As a seller, I want to create new listings with images, price, and description. | Story | Done | High | Sprint 3
4 | As a seller, I want to edit or delete my existing listings. | Story | Done | High | Sprint 3
5 | As a seller, I want to view all the items I have listed. | Story | Done | High | Sprint 3
6 | As a seller, I want to manage my listing details including title, photos, and price updates. | Story | Done | High | Sprint 3
7 | As a seller, I want to receive notifications when someone reports one of my listings. | Story | Done | High | Sprint 4
8 | As a seller, I want to sign out safely from the platform. | Story | Done | High | Sprint 1

## Admin
# | User Story Summary | Issue Type | Status | Priority | Sprint | Comment
1 | As an admin, I want to log in using admin credentials. | Story | Done | High | Sprint 1
2 | As an admin, I want to view all product listings. | Story | Done | High | Sprint 4
3 | As an admin, I want to be able to remove inappropriate listings. | Story | Done | High | Sprint 4
4 | As an admin, I want to see flagged or reported listings with details. | Story | Done | High | Sprint 4
5 | As an admin, I want to approve or reject suspicious listings. | Story | Done | High | Sprint 4
6 | As an admin, I want to notify sellers when their listing is approved or rejected. | Story | Done | High | Sprint 4
7 | As an admin, I want to view a dashboard of total users, listings, and reports. | Story | Done | High | Sprint 4
8 | As an admin, I want to log out safely from the application. | Story | Done | High | Sprint 1

## Sprint 1
Start Date - September 14, 2025
End Date - September 28, 2025
Objective - Establish the foundational project structure for CampusHub, including GitHub setup, backend and frontend scaffolding, initial database planning, and UI wireframes. Ensure the team is aligned on architecture and development workflow.
# | Task | Assignee | Status | Priority
1 | Create project plan. | All | Done | High
2 | Create project setup in local. | All | Done | High
3 | Discuss and define technology stack. | All | Done | High
4 | Design application wireframes for Customer, Seller, and Admin workflows. | Tanisha | Done | High
5 | Create User Story documents for Customer, Seller, and Admin. | Neeraja | Done | High
6 | Plan all scrum meetings and create the sprint plan. | Deven | Done | High
7 | RnD on cloud platforms (render, AWS, etc.). | Yug | Done | Medium
8 | RnD on external service integrations (S3, WebSocket, Gemini AI). | Neeraja | Done | Medium
9 | Create API for user login. | Yug | Done | High
10 | Implement JWT-based authentication service. | Yug | Done | High
11 | Implement role-based login and logout functionality. | Yug | Done | High
12 | Design Login page UI with email/password fields. | Deven | Done | High
13 | Design simple home page for user navigation. | Deven | Done | Medium
14 | Add Logout button to UI and integrate logout flow. | Tanisha | Done | High
15 | Design User Signup form UI. | Tanisha | Done | High
16 | Create User Signup API. | Tanisha | Done | High

## Sprint 2
Start Date - September 29, 2025
End Date - October 12, 2025
Objective - Establish the foundational project structure for CampusHub, including GitHub setup, backend and frontend scaffolding, initial database planning, and UI wireframes. Ensure the team is aligned on architecture and development workflow.
# | Task Summary | Assignee | Status | Priority
1 | Implement authentication APIs (signup & login). | Yug | Done | High
2 | Integrate JWT authentication into backend services. | Yug | Done | High
3 | Build frontend Signup page UI. | Tanisha | Done | High
4 | Build frontend Login page and error handling. | Tanisha | Done | High
5 | Develop Landing Page UI and initial navigation. | Deven | Done | High
6 | Refine Sell Item page UI for responsiveness. | Tanisha | Done | Medium
7 | Refine Browse page UI layout and filters. | Tanisha | Done | Medium
8 | Set up API client structure in frontend. | Deven | Done | High
9 | Integrate mock API responses for early testing. | Deven | Done | Medium
10 | Implement S3 image fetch flow (backend + frontend coordination). | Yug | Done | High
11 | Fix token handling and session persistence issues in backend. | Neeraja | Done | Medium
12 | Connect authentication UI with backend APIs. | Tanisha, Deven | Done | High
13 | Test full login → dashboard flow and fix UI bugs. | Deven | Done | High

## Sprint 3
Start Date - October 13, 2025
End Date - October 26, 2025
Objective - Develop full marketplace listing features, including listing creation, details page, S3 image upload flow, and API client alignment. Solidify core marketplace operations and ensure end-to-end functionality for listings.
# | Task Summary | Assignee | Status | Priority
1 | Implement product listing creation API (title, price, condition, description). | Yug | Done | High
2 | Implement listing details API (fetch single listing with seller info). | Yug | Done | High
3 | Implement S3 presigned URL image upload flow (backend). | Yug | Done | High
4 | Build frontend Sell Item page with image upload UI. | Tanisha | Done | High
5 | Build Listing Details page with dynamic rendering. | Deven | Done | High
6 | Integrate image upload UI with backend S3 upload endpoint. | Tanisha | Done | High
7 | Update frontend API client after backend adjustments. | Deven | Done | High
| Add listing editing & delete support in backend. | Neeraja | Done | Medium
| Add edit/delete buttons and UI interactions for listings. | Tanisha | Done | Medium
| Improve backend validation for listing creation/update. | Neeraja | Done | Medium
| Polish UI for listing cards and grids. | Deven | Done | Medium
| Conduct integration testing of create → view → update listing flow. | Deven, Yug | Done | High

## Sprint 4
Start Date - October 27, 2025
End Date - November 9, 2025
Objective - Establish the foundational project structure for CampusHub, including GitHub setup, backend and frontend scaffolding, initial database planning, and UI wireframes. Ensure the team is aligned on architecture and development workflow.
# | Task Summary | Assignee | Status | Priority
1 | Implement WebSocket server for AI chatbot communication. | Neeraja | Done | High
2 | Integrate Gemini API for chatbot response generation. | Neeraja | Done | High
3 | Create backend handler for chatbot message routing & WS events. | Neeraja | Done | High
4 | Build frontend Chatbot UI layout. | Deven | Done | High
5 | Integrate frontend chat interface with WebSocket backend. | Tanisha | Done | High
6 | Improve product listing UI responsiveness and layout. | Tanisha | Done | Medium
7 | Refine image upload process (validation, multiple file support). | Yug | Done | Medium
8 | Fix WebSocket port configuration & connection stability issues. | Neeraja | Done | Medium
9 | Implement Admin review & moderation APIs (flagged listings). | Yug | Done | High
10 | Create Admin UI skeleton for viewing flagged listings. | Deven | Done | Medium
11 | Test chatbot → listing recommendation flow. | Deven, Neeraja | Done | High

## Sprint 5
Start Date - November 10, 2025
End Date - November 23, 2025
Objective - Integrate chatbot UI with backend WebSocket services, finalize listing UI polish, complete compatibility fixes, and conduct major integration testing across listings, chat, and navigation. Prepare the application for final testing.
# | Task Summary | Assignee | Status | Priority
1 | Finalize chatbot UI and fully connect WebSocket messaging. | Deven | Done | High
2 | Merge WebSocket feature branch into main backend codebase. | Yug | Done | High
3 | Improve Listing Page UI (card grid, spacing, filters). | Tanisha | Done | High
4 | Improve Listing Details Page UI (image gallery, seller info). | Tanisha | Done | High
5 | Fix frontend API client compatibility with updated backend responses. | Deven | Done | High
6 | Conduct integration testing: create → view → chat → admin flow. | Deven, Yug | Done | High
7 | Add consistent error-handling and toast messages across frontend. | Tanisha | Done | Medium
8 | Clean up unused mock APIs and remove redundant frontend code. | Deven | Done | Medium
9 | Optimize listing API performance and handle edge cases. | Yug | Done | Medium
10 | Fix minor backend bugs discovered during integration tests. | Neeraja | Done | High

## Sprint 6
Start Date - November 24, 2025
End Date - November 30, 2025
Objective - Complete full system validation, cloud testing, and bug fixes. Finalize all project documentation, polish UI for presentation, rehearse the demo, and prepare the final release version of CampusHub.
# | Task Summary | Assignee | Status | Priority
1 | Perform final cloud testing for backend, frontend, and WebSocket services. | Yug | Done | High
2 | Conduct end-to-end testing for all user flows (auth → listing → chat → admin). | Deven, Yug | Done | High
3 | Fix final backend bugs (navigation issues, chat reconnect logic, error cases). | Yug | Done | High
4 | Fix final frontend bugs (UI glitches, error banners, layout issues). | Tanisha | Done | High
5 | Finalize all project documentation (Scrum Report, XP Values, Backlogs, Burndown). | Neeraja | Done | High
6 | Generate UI Wireframes, Component Diagram, Deployment Diagram. | Tanisha | Done | Medium
7 | Finalize README with setup instructions and architecture overview. | Deven | Done | Medium
8 | UI polish across pages for the final demo (spacing, colors, transitions). | Tanisha | Done | Medium
9 | Rehearse final project demo and complete presentation slides. | All | Done | Medium
10 | Archive final GitHub release and close project. | All | Done | Medium